## Sheet1 (hidden)
BLUE - Input current year information
RED - Input prior year information
BLACK - FORMULAS PLEASE DO NOT CHANGE

## Sheet2
|  | COMPLETED SAMPLE WORK-IN-PROGRESS SCHEDULE - EXCEL SPREADSHEET | [5 empty] | 8
|  | Managements Current Estimate of: | [8 empty] | GROSS PROFIT (LOSS) |  |  |  |  | CURRENT COSTS
|  |  | Total | Total |  |  |  | Earned | Direct | Gross | [8 empty] | Applied | Applied |  | Prior | Direct |  | Total |  |  |  |  | Prior | WIP
|  | Total | Direct | Gross |  | Contract | Under | Contract | Contract | Profit | Earned | Earned | Gross | [5 empty] | Labor | Equip | Total | Period | Contract | Estimated | Direct | Estimated |  |  | Prior | Costs & | Prior
Contract | WIP=1 | Contract | Contract | Profit | Percent | Billings | (Over) | Revenue | Costs | (LOSS) | Prior | Current | Profit | [5 empty] | Costs | Costs | Current | Direct | Costs | Costs to | Contract | Gross | Under | Over | Year | Billings | Period
Description | Com=2 | Revenue | Costs | (LOSS) | Complete | To Date | Billings | To Date | To Date | To Date | Period | Period | Percentage | Labor | Materials | Subs | Equipment | Other | 0 | 0 | Costs | Costs | To Date | Complete | Costs | Profits | Billings | Billings | Billings | In Excess | Costs
Contract | 1 | 750000 | 585000 | 165000 | 59% | 100000 | 344850 | 444850 | 347500 | 97350 | 100000 | -2650 | 22% | 25000 | 300000 | 0 | 0 | 22500 | 0 | 0 | 347500 | 0 | 347500 | 237500 | 585000 | 165000 | 344850 | 0 | 0 | 0 | 0
Contract | 1 | 42837 | 32837 | 10000 | 24% | 10750 | -550 | 10200 | 7800 | 2400 |  | 2400 | 23.34% | 0 | 0 | 0 | 0 | 7800 | 0 | 0 | 7800 | 0 | 7800 | 25037 | 32837 | 10000 | 0 | -550 | 0 |  | 0
Contract | 1 | 2047219 | 1734219 | 313000 | 29% | 296372.36 | 293125.22 | 589497.58 | 498727.58 | 90770 | 0 | 90770 | 15.29% | 26664.84 | 4930.83 | 452041.92 | 5056.25 | 10033.74 | 0 | 0 | 498727.58 | 0 | 498727.58 | 1235491.42 | 1734219 | 313000 | 293125 | 0 | 0 | 0 | 0
Contract | 1 | 258000 | 250500 | 7500 | 37% | 95399.5 | 403.96 | 95803.46 | 93028.46 | 2775 | 3960 | -1185 | 2.907% | 42503.46 | 23581 | 0 | 3486 | 100 | 0 | 0 | 69670.46 | 23358 | 93028.46 | 157471.54 | 250500 | 7500 | 404 | 0 | 20800 | 6518 | 23358
Contract | 1 | 85076 | 74866.88 | 10209.12 | 73% | 50203.69 | 12105.91 | 62309.6 | 54856.6 | 7453 |  | 7453 | 12% | 28812.98 | 8004.46 | 15370 | 1060.09 | 1609.07 | 0 | 0 | 54856.6 | 0 | 54856.6 | 20010.28 | 74866.88 | 10209.12 | 12106 | 0 | 0 | 0 | 0
Contract | 1 | 250508.47 | 195508.47 | 55000 | 74% | 203455.47 | -18417.92 | 185037.55 | 144337.55 | 40700 | 3750 | 36950 | 21.96% | 37250 | 16362.27 | 56429 | 234 | 7767.28 | 0 | 0 | 118042.55 | 26295 | 144337.55 | 51170.92 | 195508.47 | 55000 | 0 | -18418 | 72800 | -42755 | 26295
Contract | 1 | 452596.77 | 407596.77 | 45000 | 83% | 352026.87 | 25298.32 | 377325.19 | 339975.19 | 37350 | 4050 | 33300 | 9.943% | 67957.41 | 113111.04 | 22964.83 | 91602 | 6863.91 | 0 | 0 | 302499.19 | 37476 | 339975.19 | 67621.58 | 407596.77 | 45000 | 25298 | 0 | 0 | 41526 | 37476
Contract | 1 | 1112968 | 979968 | 133000 | 90% | 896801.95 | 108294.15 | 1005096.1 | 885396.1 | 119700 | 0 | 119700 | 11.95% | 71465.38 | 176258.14 | 440523.31 | 125990.71 | 31717.56 | 0 | 0 | 845955.1 | 39441 | 885396.1 | 94571.9 | 979968 | 133000 | 108294 | 0 | 95815 | -56374 | 39441
Contract | 1 | 337859 | 357859 | -20000 | 98% | 300087 | 31175 | 331262 | 351262 | -20000 | -35000 | 15000 | 0% | 19645 | 2361 | 4085 | 2238 | 240 | 0 | 0 | 28569 | 322693 | 351262 | 6597 | 357859 | -20000 | 31175 | 0 | 255466 | 32227 | 322693
Contract | 2 | 158191 | 126191 | 32000 | 100% | 158191 | 472 | 158663 | 126663 | 32000 | 18400 | 13600 | 20.23% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126663 | 126663 | -472 | 126191 | 32000 | 472 | 0 | 147491 | -2428 | 0
Contract | 2 | 12818 | 4918 | 7900 | 100% | 12818 | -24 | 12794 | 4894 | 7900 | 550 | 7350 | 61.63% | 278 | 82 | 0 | 1327 | 0 | 0 | 0 | 1687 | 3207 | 4894 | 24 | 4918 | 7900 | 0 | -24 | 12818 | -9061 | 0
Contract | 2 | 941013.77 | 468013.77 | 473000 | 100% | 941013.77 | 565.53 | 941579.3 | 468579.3 | 473000 | 243780 | 229220 | 50.26% | 131511 | 114083.36 | 0 | 7623.94 | 77 | 0 | 0 | 253295.3 | 215284 | 468579.3 | -565.53 | 468013.77 | 473000 | 566 | 0 | 402468 | 56596 | 0
Contract | 2 | 536191.32 | 376191.32 | 160000 | 100% | 536191 | -894.7 | 535296.3 | 375296.3 | 160000 | 73750 | 86250 | 29.84% | 23380.95 | 7442 | 23580.35 | 683 | 1903 | 0 | 0 | 56989.3 | 318307 | 375296.3 | 895.02 | 376191.32 | 160000 | 0 | -895 | 423590 | -31533 | 0
Contract | 2 | 714262.84 | 556262.84 | 158000 | 100% | 714263 | -2271.15 | 711991.85 | 553991.85 | 158000 | 27950 | 130050 | 22.12% | 32402.5 | 16753.34 | 3326 | 569.1 | 4118.91 | 0 | 0 | 57169.85 | 496822 | 553991.85 | 2270.99 | 556262.84 | 158000 | 0 | -2271 | 621602 | -96830 | 0
Contract
Contract | 1 | 78935 | 63935 | 15000 | 43% | 44000 | -9833 | 34167 | 27717 | 6450 | 0 | 6450 | 19% | 0 | 0 | 0 | 0 | 27717 | 0 | 0 | 27717 | 0 | 27717 | 36218 | 63935 | 15000 | 0 | 0 | 0 | 0 | 0
|  | 7778476.17 | 6213867.05 | 1564609.12 |  | 4711573.61 | 784299.32 | 5495872.93 | 4280024.93 | 1215848 | 441190 | 774658 |  | 506871.52 | 782969.44 | 1018320.41 | 239870.09 | 122447.47 | 0 | 0 | 2670478.93 | 1609546 | 4280024.93 | 1933842.12 | 6213867.05 | 1564609.12 | 816290 | -22158 | 2052850 | -102114 | 449263
[6 empty] | Prior Year Amounts |  | 2050736 | 1609546 | 441190 | 21.51%
[6 empty] | Current Year Amounts |  | 3445136.93 | 2670478.93 | 774658 | 22.49%
[6 empty] | Per GL |  | 3336590.32 | 2061365 | 1275225.32
[6 empty] | Difference: |  | 108546.61 | 609114.43 | -500567.32
|  |  |  | Costs in excess of billings |  |  | 816290
|  |  |  | Billings in excess of costs |  |  | -22158
794132

## WIP (hidden)
#REF!
Construction Contracts in Progress
#REF!
GROSS PROFIT (LOSS)
|  |  | Total | Total |  |  |  | Earned | Direct | Gross
|  | Total | Direct | Gross |  | Contract | Under | Contract | Contract | Profit | Earned | Earned
Contract | Contract | Contract | Contract | Profit | Percent | Billings | (Over) | Revenue | Costs | (LOSS) | Prior | Current
# | Description | Revenue | Costs | (LOSS) | Complete | To Date | Billings | To Date | To Date | To Date | Period | Period
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | Recognized in prior period |  |  | #REF! | #REF! | #REF!
[8 empty] | #REF! | #REF! | #REF!
|  |  |  | Costs in excess of billings |  | #REF!
|  |  |  | Billings in excess of cost |  | #REF!
#REF!

## COMPLETED (hidden)
#REF!
Construction Contracts Completed
#REF!
|  |  | Total | Total
|  | Total | Direct | Gross | Earned | Earned
Contract | Contract | Contract | Contract | Profit | Prior | Current
# | Description | Revenue | Costs | (LOSS) | Period | Period
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #VALUE! | #REF!
|  | #REF! | #REF! | #REF!

## EARNINGS (hidden)
#REF!
Earnings From Construction Contracts
#REF!
Total
| Total | Direct | Total
| Contract | Contract | Gross
| Revenue | Costs | Profit
Construction Contracts Completed | #REF! | #REF! | #REF! | #REF!
Construction Contracts in Progress | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!

## BACKLOG (hidden)
10. CONTRACT BACKLOG
The following schedule is a reconciliation of contract backlog representing signed contracts as
of December 31, 2006
| Contract | Estimated | Estimated
| Revenue | Direct Costs | Gross Profit
Balance, January 1, 2006
New contracts and adjustments during the year | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE!
Earned during the year | #REF! | #REF! | #REF!
Balance, December 31, 2006 | #VALUE! | #VALUE! | #VALUE!

## OVERUNDERBILLINGS (hidden)
4. COSTS AND ESTIMATED EARNINGS ON CONSTRUCTION CONTRACTS IN PROGRESS
Costs and estimated earnings on construction contracts in progress contrast related billings
follows:
Direct contract costs to date | #REF!
Gross profit to date | #REF!
Earned contract revenue | #REF!
Contract billings to date | #REF!
Net over under billings | #REF!
Included in the accompanying balance sheet under the following captions:
Costs and estimated earnings in excess of billings | #REF!
Billings in exess of costs and estimated earnings | #REF!
Net over under billings | #REF!